Method of Procedure (MOP)

Cisco ASR9904 — IOS XR Upgrade 24.3.2 → 25.2.2

| Procedure | IOS XR 25.2.2 upgrade on Cisco ASR9904 |
| --- | --- |
| Customer | Howard County Broadband Network (HCBN) |
| Prepared by | Skyline Technology Solutions |
| Maintenance Window | [Insert Date / Time] |
| Devices Affected | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |
| Current Version | Cisco IOS XR Software, Version 24.3.2 |
| Target Version | Cisco IOS XR Software, Version 25.2.2 |
| Upgrade Type | Single-step direct upgrade — validated: no Bridge SMUs, no caveats |

Brief Description of Work

Upgrade the Howard County Broadband Network (HCBN) Cisco ASR9904 routers (POD-ASR9904-W-01 and LIGON-ASR9904-W-01) from Cisco IOS XR 24.3.2 to 25.2.2 using the Cisco install (add / prepare / activate / commit) process. Production traffic is migrated onto the peer router before each router is upgraded, so customer impact is limited to the brief BGP re-convergence during each traffic migration.

Any discrepancies should be written in the Comments section at the end of this procedure.

NOTE: REUSABLE MOP. For a future single-step upgrade (e.g. 25.2.2 → a later release): (1) update the version strings and image name in this document; (2) re-run the upgrade-path validation (Step P-4) with the new .iso to confirm the direct path and any Bridge SMUs/caveats; (3) confirm the package/RPM set and MD5s against that release's Cisco ASR 9000 release notes.

Event Documentation

| Date (MM/DD/YY) | [Insert] |
| --- | --- |
| Net Suite Case # | TBD |
| CMMS ID # |  |
| CMMS WO # |  |

Participants

| Name / Role | Company / Title | Email | Phone |
| --- | --- | --- | --- |
| Andrew Ntuyo / Senior Network Engineer | Skyline Technology Solutions | antuyo@skylinenet.net |  |
| Haseeb Hameed / Network Architect | Skyline Technology Solutions | hhameed@skylinenet.net |  |
| Matt Smith / Chief Network Architect | Skyline Technology Solutions | msmith@skylinenet.net |  |
| Nathan Miller / Broadband Network Engineer | Howard County Office of Broadband | nmiller@howardcountymd.gov |  |
| HCBN NOC / Service Desk | Howard County Office of Broadband |  |  |

References / Supporting Documentation

Documents required on hand for execution:

| Cisco ASR 9000 IOS XR 25.2.2 Release Notes (supported software packages) | https://www.cisco.com/c/en/us/td/docs/routers/iosxr/release-notes/25xx/cisco-asr-9000-series-routers-release-notes-2522.html |
| --- | --- |
| Target image | asr9k-mini-x64-25.2.2.iso (+ any feature RPMs required by features in use — confirm against the release notes) |

Documents used in the creation of this procedure:

| IOS XR 25.2.2 Upgrade Path Validation for the ASRs | Skyline / Howard County, validated 2026-08-06 — direct upgrade supported, no Bridge SMUs |
| --- | --- |
| HCG ASR9904 Traffic Migration Script (Summary Version) | Haseeb Hameed — LIGON ⇄ POD production failover |
| ASR9904 IOS XR Upgrade MOP v2 | Prior single-step upgrade to 24.3.2 (install-process reference) |

Procedure Risks

| Risks to personnel safety | None |
| --- | --- |
| Risks to critical load | N/A |
| Risks to site | Temporary loss of redundancy during each router upgrade; brief BGP re-convergence at each traffic migration. No outage expected while the peer router carries production. |

Important Indicators

| Change of state | A step that changes the running state (config commit, activation, reload). |
| --- | --- |
| Stop & validate | Do not proceed until the expected result is confirmed. |
| Important note | Critical caveat for the step. |
| Rollback | Rollback trigger / action. |

Acronyms: MOP – Method of Procedure · SMU – Software Maintenance Update · FPD – Field-Programmable Device · RSP – Route Switch Processor · VRRP – Virtual Router Redundancy Protocol · CAB – Change Advisory Board · HCBN – Howard County Broadband Network.

Operating Procedure

1. Pre-Work and Mitigation (reusable)

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| P-1 | Remote | N/A |  | Prepare this MOP. | AN |
| P-2 | Remote | N/A |  | Submit the maintenance to CAB / change control for review; obtain approval. |  |
| P-3 | Remote | N/A |  | Issue a maintenance notification to HCBN and affected customers. Impact: temporary loss of redundancy; brief interruption possible during traffic migration. |  |
| P-4 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Stop & validate | Validate the upgrade path (read-only, non-disruptive) on BOTH routers. Download asr9k-mini-x64-25.2.2.iso, copy to harddisk:, and confirm it is present: dir harddisk: Run the upgrade matrix check against the running software: show install upgrade-matrix iso harddisk:/asr9k-mini-x64-25.2.2.iso from-running Expected result (validated 2026-08-06): Upgrade from the current software [24.3.2] to 25.2.2 is supported From To Bridge SMUs Required Caveats 24.3.2 25.2.2 None None NOTE: If the matrix reports a required Bridge SMU or an intermediate release, STOP and re-plan — this MOP assumes a validated direct path. |  |
| P-5 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |  | Download the target image and any required feature RPMs (per the 25.2.2 release notes) and verify integrity: show md5 file harddisk:/asr9k-mini-x64-25.2.2.iso |  |
| P-6 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Important note | Confirm out-of-band / console access to both routers before proceeding. Do not start the upgrade without a verified OOB path — the activate step reloads the router. |  |
| P-7 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Stop & validate | Collect PRE-upgrade baselines on BOTH routers (retain for comparison): show platform show platform vm show redundancy show install active admin show install active show install committed show version cfs check show hw-module fpd show pfm location all show alarm admin show environment all admin show led show media show inventory show logging last 200 show bgp summary show bgp ipv4 unicast summary show ospf neighbor show route summary show interfaces description show interfaces Bundle-Ether200 brief show vrrp brief |  |
| P-8 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |  | Back up the running configuration on BOTH routers (on-box and off-box): copy running-config harddisk:/pre_25.2.2_running.cfg scp harddisk:/pre_25.2.2_running.cfg <user>@<server>:/<path>/ |  |
| P-9 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |  | Reclaim disk space on BOTH routers and verify free space: install remove inactive all show media |  |
| P-10 | Remote | N/A |  | Notify the Service Desk that the case is starting. |  |

Stage Summary: Pre-Work and mitigation complete; direct upgrade path validated on both routers.

2. Migrate production traffic off LIGON onto POD

NOTE: Reconcile the Bundle-Ether200 subinterface list below to services STILL in production on the ASRs before execution — some services were migrated to the MX platform (per Matt Smith, 2026-09-01). Remove any subinterface no longer carried by the ASRs.

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| M-1 | Remote | LIGON-ASR9904-W-01 | Change of state | On LIGON — shut the production bundle and its eBGP/customer sessions: configure terminal interface Bundle-Ether200 shutdown router bgp 26297 neighbor 167.102.23.128 shutdown neighbor 167.102.188.62 shutdown neighbor 167.102.188.114 shutdown neighbor 10.196.224.1 shutdown commit end |  |
| M-2 | Remote | POD-ASR9904-W-01 | Change of state | Immediately on POD — bring up the production subinterfaces: configure terminal interface Bundle-Ether200.990 no shutdown interface Bundle-Ether200.991 no shutdown interface Bundle-Ether200.992 no shutdown interface Bundle-Ether200.993 no shutdown interface Bundle-Ether200.1110 no shutdown interface Bundle-Ether200.1201 no shutdown interface Bundle-Ether200.1202 no shutdown interface Bundle-Ether200.1206 no shutdown interface Bundle-Ether200.1207 no shutdown interface Bundle-Ether200.1209 no shutdown interface Bundle-Ether200.1210 no shutdown interface Bundle-Ether200.1212 no shutdown interface Bundle-Ether200.1214 no shutdown interface Bundle-Ether200.1216 no shutdown interface Bundle-Ether200.1219 no shutdown interface Bundle-Ether200.1220 no shutdown interface Bundle-Ether200.1215 no shutdown interface Bundle-Ether200.1250 no shutdown interface Bundle-Ether200.1255 no shutdown interface Bundle-Ether200.1263 no shutdown interface Bundle-Ether200.1264 no shutdown interface Bundle-Ether200.1266 no shutdown interface Bundle-Ether200.1269 no shutdown interface Bundle-Ether200.1271 no shutdown interface Bundle-Ether200.1272 no shutdown interface Bundle-Ether200.1273 no shutdown interface Bundle-Ether200.1274 no shutdown interface Bundle-Ether200.1275 no shutdown interface Bundle-Ether200.1281 no shutdown interface Bundle-Ether200.1284 no shutdown interface Bundle-Ether200.1286 no shutdown interface Bundle-Ether200.1288 no shutdown interface Bundle-Ether200.1310 no shutdown interface Bundle-Ether200.1311 no shutdown commit end |  |
| M-3 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Stop & validate | Confirm production is now carried by POD; capture and compare to the pre-migration capture: show bgp summary show interfaces Bundle-Ether200 brief show ospf neighbor show route <customer-prefix> detail show vrrp brief Expected: POD advertising/receiving the customer prefixes; LIGON idle; pings to test hosts clean. |  |

3. Upgrade LIGON-ASR9904-W-01 to 25.2.2 (LIGON now idle)

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| L-1 | Remote | LIGON-ASR9904-W-01 |  | Add the target image (and any required feature RPMs per the release notes) install add source harddisk:/ asr9k-mini-x64-25.2.2.iso |  |
| L-2 | Remote | LIGON-ASR9904-W-01 | Stop & validate | Retrieve the operation ID; wait for the add to complete: show install request |  |
| L-3 | Remote | LIGON-ASR9904-W-01 |  | Prepare the packages to be activated: install prepare id <ID from previous step> |  |
| L-4 | Remote | LIGON-ASR9904-W-01 | Change of state | Activate — the router reloads (~25–30 min): install activate id <ID> NOTE: Monitor the reload via the console/OOB path. Do not disconnect. |  |
| L-5 | Remote | LIGON-ASR9904-W-01 | Stop & validate | Verify the router came back on 25.2.2: show version show platform show install active show redundancy show configuration failed startup Expected: Version 25.2.2; all nodes/RSPs IOS XR RUN; redundancy ready; no failed config. |  |
| L-6 | Remote | LIGON-ASR9904-W-01 | Important note | Check FPDs; upgrade if any are not CURRENT, then reload the affected location if prompted: show hw-module fpd upgrade hw-module fpd all location all |  |
| L-7 | Remote | LIGON-ASR9904-W-01 | Important note | Commit the software: install commit NOTE: If install commit is NOT run, a reload reverts the router to 24.3.2. |  |
| L-8 | Remote | LIGON-ASR9904-W-01 |  | Remove inactive packages: install remove inactive all |  |
| L-9 | Remote | LIGON-ASR9904-W-01 | Stop & validate | Collect POST baselines and COMPARE to the pre-upgrade capture (Step P-7): show platform show platform vm show redundancy show install active admin show install active show install committed show version cfs check show hw-module fpd show pfm location all show alarm admin show environment all admin show led show media show inventory show logging last 200 show bgp summary show bgp ipv4 unicast summary show ospf neighbor show route summary show interfaces description show interfaces Bundle-Ether200 brief show vrrp brief Expected: BGP/OSPF neighbors re-established, route counts within range, no new alarms, interfaces as before. |  |

Step Summary: LIGON-ASR9904-W-01 upgraded to 25.2.2 and committed.

4. Migrate traffic back to standard (LIGON active) — this idles POD

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| B-1 | Remote | POD-ASR9904-W-01 | Change of state | On POD — shut the production subinterfaces: configure terminal interface Bundle-Ether200.990 shutdown interface Bundle-Ether200.991 shutdown interface Bundle-Ether200.992 shutdown interface Bundle-Ether200.993 shutdown interface Bundle-Ether200.1110 shutdown interface Bundle-Ether200.1201 shutdown interface Bundle-Ether200.1202 shutdown interface Bundle-Ether200.1206 shutdown interface Bundle-Ether200.1207 shutdown interface Bundle-Ether200.1209 shutdown interface Bundle-Ether200.1210 shutdown interface Bundle-Ether200.1212 shutdown interface Bundle-Ether200.1214 shutdown interface Bundle-Ether200.1216 shutdown interface Bundle-Ether200.1219 shutdown interface Bundle-Ether200.1220 shutdown interface Bundle-Ether200.1215 shutdown interface Bundle-Ether200.1250 shutdown interface Bundle-Ether200.1255 shutdown interface Bundle-Ether200.1263 shutdown interface Bundle-Ether200.1264 shutdown interface Bundle-Ether200.1266 shutdown interface Bundle-Ether200.1269 shutdown interface Bundle-Ether200.1271 shutdown interface Bundle-Ether200.1272 shutdown interface Bundle-Ether200.1273 shutdown interface Bundle-Ether200.1274 shutdown interface Bundle-Ether200.1275 shutdown interface Bundle-Ether200.1281 shutdown interface Bundle-Ether200.1284 shutdown interface Bundle-Ether200.1286 shutdown interface Bundle-Ether200.1288 shutdown interface Bundle-Ether200.1310 shutdown interface Bundle-Ether200.1311 shutdown commit end |  |
| B-2 | Remote | LIGON-ASR9904-W-01 | Change of state | Immediately on LIGON — restore the production bundle and its sessions: configure terminal interface Bundle-Ether200 no shutdown router bgp 26297 neighbor 167.102.23.128 no shutdown neighbor 167.102.188.62 no shutdown neighbor 167.102.188.114 no shutdown neighbor 10.196.224.1 no shutdown commit end |  |
| B-3 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Stop & validate | Confirm LIGON (on new code) is carrying production and POD is now idle: show bgp summary show interfaces Bundle-Ether200 brief show ospf neighbor show route <customer-prefix> detail show vrrp brief Expected: LIGON advertising/receiving customer prefixes on 25.2.2; POD idle; pings clean. |  |

5. Upgrade POD-ASR9904-W-01 to 25.2.2 (POD now idle)

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| P2-1 | Remote | POD-ASR9904-W-01 |  | Add the target image (and any required feature RPMs per the release notes) install add source harddisk:/ asr9k-mini-x64-25.2.2.iso |  |
| P2-2 | Remote | POD-ASR9904-W-01 | Stop & validate | Retrieve the operation ID; wait for the add to complete: show install request |  |
| P2-3 | Remote | POD-ASR9904-W-01 |  | Prepare the packages to be activated: install prepare id <ID from previous step> |  |
| P2-4 | Remote | POD-ASR9904-W-01 | Change of state | Activate — the router reloads (~25–30 min): install activate id <ID> NOTE: Monitor the reload via the console/OOB path. Do not disconnect. |  |
| P2-5 | Remote | POD-ASR9904-W-01 | Stop & validate | Verify the router came back on 25.2.2: show version show platform show install active show redundancy show configuration failed startup Expected: Version 25.2.2; all nodes/RSPs IOS XR RUN; redundancy ready; no failed config. |  |
| P2-6 | Remote | POD-ASR9904-W-01 | Important note | Check FPDs; upgrade if any are not CURRENT, then reload the affected location if prompted: show hw-module fpd upgrade hw-module fpd all location all |  |
| P2-7 | Remote | POD-ASR9904-W-01 | Important note | Commit the software: install commit NOTE: If install commit is NOT run, a reload reverts the router to 24.3.2. |  |
| P2-8 | Remote | POD-ASR9904-W-01 |  | Remove inactive packages: install remove inactive all |  |
| P2-9 | Remote | POD-ASR9904-W-01 | Stop & validate | Collect POST baselines and COMPARE to the pre-upgrade capture (Step P-7): show platform show platform vm show redundancy show install active admin show install active show install committed show version cfs check show hw-module fpd show pfm location all show alarm admin show environment all admin show led show media show inventory show logging last 200 show bgp summary show bgp ipv4 unicast summary show ospf neighbor show route summary show interfaces description show interfaces Bundle-Ether200 brief show vrrp brief Expected: BGP/OSPF neighbors re-established, route counts within range, no new alarms, interfaces as before. |  |

Step Summary: POD-ASR9904-W-01 upgraded to 25.2.2 and committed.

6. Restore standard state & full redundancy

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| R-1 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Stop & validate | Confirm both routers are on 25.2.2 and healthy, with redundancy restored to the normal design: show version show redundancy show bgp summary show ospf neighbor show vrrp brief show interfaces Bundle-Ether200 brief Expected: both routers 25.2.2; BGP/OSPF/VRRP normal; production balanced per standard design; pings clean. |  |

Completion Steps

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| C-1 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |  | Verify logs and alarms are clean on both routers (show logging, show alarm). |  |
| C-2 | NMS | HCBN NMS |  | Verify NMS alerts have recovered and both devices/ports are re-discovered. |  |
| C-3 | Remote | N/A |  | Notify the Service Desk that the case is complete. |  |

Stage Summary: Post-maintenance tasks completed.

Roll Back Section

| Step | Location | Equipment | Indicator | Action / Task | Init |
| --- | --- | --- | --- | --- | --- |
| RB-1 | Remote | Target router | Rollback | Pre-commit: reload reverts automatically. If the upgrade has NOT been committed, reload the router to revert to 24.3.2: reload location all |  |
| RB-2 | Remote | Target router | Rollback | Post-commit: reinstall the previous release. install add source harddisk:/asr9k-mini-x64-24.3.2.iso install prepare id <ID> install activate id <ID> noprompt install commit |  |
| RB-3 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 | Rollback | Traffic-level rollback. If connectivity is lost during a migration step, re-run the opposite migration script to return production to the healthy router, verify connectivity, then reassess. |  |
| RB-4 | Remote | POD-ASR9904-W-01, LIGON-ASR9904-W-01 |  | General: at any step, if unexpected connectivity loss is observed or reported, roll back the last change, verify connectivity is restored, and re-evaluate the next step. |  |

Comments

Revision Control

| Revision | Date (YYYY/MM/DD) | Author | Changes made |
| --- | --- | --- | --- |
| 1.0 | 2026/09/08 | Andrew Ntuyo | Initial release |

Approval

| Revision | Date | Author | Reviewer | Approver |
| --- | --- | --- | --- | --- |
| 1.0 |  | Andrew Ntuyo | Skyline NetEng Team | Matt Smith |